## SPP Status Check - Master Sheet
Directions: Initial Setup (to be completed prior to Act 2, Event 6): Step 1: Enter your school-specific goals from your School Performance Plan - A Roadmap to Success under School Goal 1, 2, and 3. You can add or remove goals as needed. Select the NDE STIP Goal the school goal aligns with in the Connects To... drop-down menu. Step 2: For each goal, add the Improvement Strategies, Intended Outcomes, and dates for each event from the SPP Roadmap. Note: The Goals, Improvement Strategies, Intented Outcomes, and dates you enter on this tab will auto-populate the subsequent tabs. Similarly, information you enter on tabs 2-5 will automatically populate this tab.
School Goal |  | Select aligned STIP goal below: |  |  | Did we achieve our goal?
EIAA's goal for the 2021-2022 school year is to have at least a 60 for our MGP growth for both ELA and Math and a 50 AGP for growth for both ELA and Math |  | Nevada Education Goal 3: All students experience continued academic growth |  |  | 0
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Event 7: Status Check 2 (Insert Date) | Event 8: Status Check 3 (Insert Date) | Were our improvement strategies successful?
Hire 3rd party data consultant to help EIAA analyze data and identify areas of need | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5% | Strong | Strong | Strong | 0
Create individual student, data-based objectives and goals based off students' identified strengths and deficits. | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5%
Use evidence-based interventions such as Newsela, Odyssey Math, Odysseay Reading, I-ready, DRA and data-based decision making to create a plan, instrucion, and a practice based off goals and objectives. | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5% | Strong | Strong | Strong | 0
School Goal |  | Select aligned STIP goal below: |  |  | Did we achieve our goal?
Strengthen instruction by defining grade level and individual student big rocks, student objectives, and success criteria |  | Nevada Education Goal 2: All students have access to effective educators |  |  | 0
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Event 7: Status Check 2 (Insert Date) | Event 8: Status Check 3 (Insert Date) | Were our improvement strategies successful?
Provide PD on Formative Assessment through SPCSA | Improve instruction to increase student proficiency | At Risk | At Risk | At Risk | 0
Teachers work with accountability partner to unwrap standards, analyze student data, and plan next steps | Improve instruction to increase student proficiency
|  | 0 | 0 | 0 | 0
School Goal |  | Select aligned STIP goal below: |  |  | Did we achieve our goal?
Improve instruction and student proficiency through communication and connectedness |  | Nevada Education Goal 6: All students and adults learn and work together in safe environments where identities and relationships are valued and celebrated |  |  | 0
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Event 7: Status Check 2 (Insert Date) | Event 8: Status Check 3 (Insert Date) | Were our improvement strategies successful?
EIAA will create leadership binders that allow students to be an active participant within their learning process. | Work collaboratively with students and parents to improve instruction and increase student proficiency | Strong | Strong | Strong | 0
Teachers and students will share student goals with parents | Work collaboratively with students and parents to improve instruction and increase student proficiency
|  | 0 | 0 | 0 | 0
School Goal |  | Select aligned STIP goal below: |  |  | Did we achieve our goal?
(insert goal here) |  |  |  |  | 0
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Event 7: Status Check 2 (Insert Date) | Event 8: Status Check 3 (Insert Date) | Were our improvement strategies successful?
(insert improvement strategies here) | (insert intended outcomes here) | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
School Goal |  | Select aligned STIP goal below: |  |  | Did we achieve our goal?
(insert goal here) |  |  |  |  | 0
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Event 7: Status Check 2 (Insert Date) | Event 8: Status Check 3 (Insert Date) | Were our improvement strategies successful?
(insert improvement strategies here) | (insert intended outcomes here) | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0

## Event 6 Status Check 1
Directions: As a team, for each goal: Step 1: Review the Findings/Visualizations slides within the Events 6-8 slide deck. These will need to be updated prior to each event. Step 2: Reflect on the Now, Next, Need questions noted in the slide deck. Step 3: Fill in the appropriate cells for Event 6. - Rate the overall status of the improvement strategy using one of the following: Strong - on track; At Risk - requires some refinement and/or support; or Needs Immediate Attention - requires immediate support - Identify specific Lessons Learned (Now), Next Steps and Needs Note: The rating you enter for Step 3 will automatically update the accompanying cell on the Master Tracker (tab 1).
School Goal
EIAA's goal for the 2021-2022 school year is to have at least a 60 for our MGP growth for both ELA and Math and a 50 AGP for growth for both ELA and Math
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Hire 3rd party data consultant to help EIAA analyze data and identify areas of need | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5% | Strong | We have hired RTB data out of Las Vegas. They were able to meet with teachers at the beginning of the year. | Meet over winter data | Students to take winter MAP test
Create individual student, data-based objectives and goals based off students' identified strengths and deficits. | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5% | Strong | Teachers have identified student strengths and areas in need of support | Continue to analyze data and adjust interventions
Use evidence-based interventions such as Newsela, Odyssey Math, Odysseay Reading, I-ready, DRA and data-based decision making to create a plan, instrucion, and a practice based off goals and objectives. | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5% | Strong | Classrooms are currently using ESSER approved intervention programs with their students for math and ela | Continue providing students opportunities within intervention analyze winter map data
School Goal
Strengthen instruction by defining grade level and individual student big rocks, student objectives, and success criteria
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Provide PD on Formative Assessment through SPCSA | Improve instruction to increase student proficiency | At Risk | I did not relize the time line on the Formative Assessment PD from SPCSA. I did not relize this year was for admin only | Provide PD within formative assessment for the 2022-2023 school year
Teachers work with accountability partner to unwrap standards, analyze student data, and plan next steps | Improve instruction to increase student proficiency | Strong | Teachers meet at least once a week with their accountability partners | Continue to work with accountability partners to analyze data and plan accordingly | Time
0 | 0
School Goal
Improve instruction and student proficiency through communication and connectedness
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
EIAA will create leadership binders that allow students to be an active participant within their learning process. | Work collaboratively with students and parents to improve instruction and increase student proficiency | Strong | Students are all tracking their data within their classrooms. | Continue to move goals and track data with students | Time
Teachers and students will share student goals with parents | Work collaboratively with students and parents to improve instruction and increase student proficiency | Strong | We have 3 formal parent teacher conferences set up for this year plus reporting on grades 4 times throughout the year. In between formal meetings with parents, teachers are in contact with parents on a regular basis | Continue communicating with parents and looking for ways to improve or strengthen communication
0 | 0
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
0 | 0
0 | 0
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 6: Status Check 1 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
0 | 0
0 | 0

## Event 7 Status Check 2
Directions: As a team, for each goal: Step 1: Review the Findings/Visualizations slides within the Events 6-8 slide deck. These will need to be updated prior to each Event. Step 2: Reflect on the Now, Next, Need questions noted in the slide deck. Step 3: Fill in the appropriate cells for Event 7. - Rate the overall status of the improvement strategy using one of the following: Strong - on track; At Risk - requires some refinement and/or support; or Needs Immediate Attention - requires immediate support - Identify specific Lessons Learned (Now), Next Steps and Needs Note: The rating you enter for Step 3 will automatically update the accompanying cell on the Master Tracker (tab 1).
School Goal
EIAA's goal for the 2021-2022 school year is to have at least a 60 for our MGP growth for both ELA and Math and a 50 AGP for growth for both ELA and Math
Improvement Strategies | Intended Outcomes | Event 7: Status Check 2 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Hire 3rd party data consultant to help EIAA analyze data and identify areas of need | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5% | Strong | According to map winter data, our K-5 ELA prof. is up 8.4% and math 51.5% | Continue to work on student goals and interventions | Funding to keep data consultant
Create individual student, data-based objectives and goals based off students' identified strengths and deficits. | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5% | Strong | MGP for elementary ELA is 62% and AGP is 61.7%. MGP for elementary math is 47% and AGP is 41.1% | Work on math agp and mgp | Students to take SBAC for Spring 22
Use evidence-based interventions such as Newsela, Odyssey Math, Odysseay Reading, I-ready, DRA and data-based decision making to create a plan, instrucion, and a practice based off goals and objectives. | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5% | Strong | Middle School prof. is up 1.6% in ELA and 6.5% in math. MGP for Middle School ELA is 69% and AGP is 60.8%. MGP for Middle School math is 62% and AGP is 46.6%. |  | Funding to keep these ESSA approved interventions
School Goal
Strengthen instruction by defining grade level and individual student big rocks, student objectives, and success criteria
Improvement Strategies | Intended Outcomes | Event 7: Status Check 2 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Provide PD on Formative Assessment through SPCSA | Improve instruction to increase student proficiency | At Risk | I did not relize the time line on the Formative Assessment PD from SPCSA. I did not relize this year was for admin only | Provide PD within formative assessment for the 2022-2023 school year
Teachers work with accountability partner to unwrap standards, analyze student data, and plan next steps | Improve instruction to increase student proficiency | Strong | Teachers meet at least once a week with their accountability partners | Continue to work with accountability partners to analyze data and plan accordingly | Time
0 | 0
School Goal
Improve instruction and student proficiency through communication and connectedness
Improvement Strategies | Intended Outcomes | Event 7: Status Check 2 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
EIAA will create leadership binders that allow students to be an active participant within their learning process. | Work collaboratively with students and parents to improve instruction and increase student proficiency | Strong | Students are all tracking their data within their classrooms. | Continue to move goals and track data with students | Time
Teachers and students will share student goals with parents | Work collaboratively with students and parents to improve instruction and increase student proficiency | Strong | We have 3 formal parent teacher conferences set up for this year plus reporting on grades 4 times throughout the year. In between formal meetings with parents, teachers are in contact with parents on a regular basis | Continue communicating with parents and looking for ways to improve or strengthen communication
0 | 0
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 7: Status Check 2 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
0 | 0
0 | 0
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 7: Status Check 2 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
0 | 0
0 | 0

## Event 8 Status Check 3
Directions: As a team, for each goal: Step 1: Review the Findings/Visualizations slides within the Events 6-8 slide deck. These will need to be updated prior to each event. Step 2: Reflect on the Now, Next, Need questions noted in the slide deck. Step 3: Fill in the appropriate cells for Event 8. - Rate the overall status of the improvement strategy using one of the following: Strong - on track; At Risk - requires some refinement and/or support; or Needs Immediate Attention - requires immediate support - Identify specific Lessons Learned (Now), Next Steps and Needs Note: The rating you enter for Step 3 will automatically update the accompanying cell on the Master Tracker (tab 1).
School Goal
EIAA's goal for the 2021-2022 school year is to have at least a 60 for our MGP growth for both ELA and Math and a 50 AGP for growth for both ELA and Math
Improvement Strategies | Intended Outcomes | Event 8: Status Check 3 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Hire 3rd party data consultant to help EIAA analyze data and identify areas of need | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5% | Strong | According to map winter data, our K-5 ELA prof. is up 8.4% and math 51.5% | Continue to work on student goals and interventions | Funding to keep data consultant / Spring MAP Data we won't have complete until June | Spring Data is not in and waiting for SBAC Results so Check 7 and 8 has same school wide data.
Create individual student, data-based objectives and goals based off students' identified strengths and deficits. | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5% | Strong | MGP for elementary ELA is 62% and AGP is 61.7%. MGP for elementary math is 47% and AGP is 41.1% | Work on math agp and mgp | Students to take SBAC for Spring 22
Use evidence-based interventions such as Newsela, Odyssey Math, Odysseay Reading, I-ready, DRA and data-based decision making to create a plan, instrucion, and a practice based off goals and objectives. | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5% | Strong | Middle School prof. is up 1.6% in ELA and 6.5% in math. MGP for Middle School ELA is 69% and AGP is 60.8%. MGP for Middle School math is 62% and AGP is 46.6%. | Waiting for School Wide Spring Data to make next step decisions | Funding to keep these ESSA approved interventions
School Goal
Strengthen instruction by defining grade level and individual student big rocks, student objectives, and success criteria
Improvement Strategies | Intended Outcomes | Event 8: Status Check 3 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
Provide PD on Formative Assessment through SPCSA | Improve instruction to increase student proficiency | At Risk | I did not relize the time line on the Formative Assessment PD from SPCSA. I did not relize this year was for admin only | Provide PD within formative assessment for the 2022-2023 school year
Teachers work with accountability partner to unwrap standards, analyze student data, and plan next steps | Improve instruction to increase student proficiency | Strong | Teachers meet at least once a week with their accountability partners | Continue to work with accountability partners to analyze data and plan accordingly | Time
0 | 0
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 8: Status Check 3 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
EIAA will create leadership binders that allow students to be an active participant within their learning process. | Work collaboratively with students and parents to improve instruction and increase student proficiency | Strong | Students are all tracking their data within their classrooms. | Continue to move goals and track data with students | Time
Teachers and students will share student goals with parents | Work collaboratively with students and parents to improve instruction and increase student proficiency | Strong | We have 3 formal parent teacher conferences set up for this year plus reporting on grades 4 times throughout the year. In between formal meetings with parents, teachers are in contact with parents on a regular basis | Continue communicating with parents and looking for ways to improve or strengthen communication
0 | 0
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 8: Status Check 3 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
0 | 0
0 | 0
School Goal
(insert goal here)
Improvement Strategies | Intended Outcomes | Event 8: Status Check 3 (Insert Date) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
0 | 0
0 | 0

## Event 9 Reviewing Our Journey
Directions: As a team, for each Goal: Step 1: Review the Findings/Visualizations slides within the Event 9 slide deck. These will need to be updated prior to each event. Step 2: Reflect on the Now, Next, Need questions noted in the slide deck. Step 3: Fill in the appropriate cells in the table below. - Did we achieve our Goal/Intended Outcomes - Yes, No. - Do we continue, correct, or cancel our goals/implementation strategies - Continue, Correct, Cancel. - Identify specific Lessons Learned, Next Steps and Needs. Note: The rating you enter for Step 3 will automatically update the accompanying cell on the Master Tracker (tab 1).
School Goal |  | Did we achieve our goal?
EIAA's goal for the 2021-2022 school year is to have at least a 60 for our MGP growth for both ELA and Math and a 50 AGP for growth for both ELA and Math
Improvement Strategies | Intended Outcomes | Were our improvement strategies successful? (Select One) | Continue, Correct, or Cancel the Strategy? (Select One) | Now (Lessons Learned) | Next (Next Steps) | Need
Hire 3rd party data consultant to help EIAA analyze data and identify areas of need | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5%
Create individual student, data-based objectives and goals based off students' identified strengths and deficits. | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5%
Use evidence-based interventions such as Newsela, Odyssey Math, Odysseay Reading, I-ready, DRA and data-based decision making to create a plan, instrucion, and a practice based off goals and objectives. | During the SBAC assessment we will improve our student proficiency in math and ELA by a minimum of 5%
School Goal |  | Did we achieve our goal?
Strengthen instruction by defining grade level and individual student big rocks, student objectives, and success criteria
Improvement Strategies | Intended Outcomes | Were our improvement strategies successful? (Select One) | Continue, Correct, or Cancel the Strategy? (Select One) | Now (Lessons Learned) | Next (Next Steps) | Need
Provide PD on Formative Assessment through SPCSA | Improve instruction to increase student proficiency
Teachers work with accountability partner to unwrap standards, analyze student data, and plan next steps | Improve instruction to increase student proficiency
0 | 0
School Goal |  | Did we achieve our goal?
Improve instruction and student proficiency through communication and connectedness
Improvement Strategies | Intended Outcomes | Were our improvement strategies successful? (Select One) | Continue, Correct, or Cancel the Strategy? (Select One) | Now (Lessons Learned) | Next (Next Steps) | Need
EIAA will create leadership binders that allow students to be an active participant within their learning process. | Work collaboratively with students and parents to improve instruction and increase student proficiency
Teachers and students will share student goals with parents | Work collaboratively with students and parents to improve instruction and increase student proficiency
0 | 0
School Goal |  | Did we achieve our goal?
(insert goal here)
Improvement Strategies | Intended Outcomes | Were our improvement strategies successful? (Select One) | Continue, Correct, or Cancel the Strategy? (Select One) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
0 | 0
0 | 0
School Goal |  | Did we achieve our goal?
(insert goal here)
Improvement Strategies | Intended Outcomes | Were our improvement strategies successful? (Select One) | Continue, Correct, or Cancel the Strategy? (Select One) | Now (Lessons Learned) | Next (Next Steps) | Need
(insert improvement strategies here) | (insert intended outcomes here)
0 | 0
0 | 0

## For Lists (hidden)
Nevada Education Goal 1: All children birth through third grade have access to quality early care and education
Nevada Education Goal 2: All students have access to effective educators
Nevada Education Goal 3: All students experience continued academic growth
Nevada Education Goal 4: All students graduate future-ready and globally prepared for postsecondary success and civic life
Nevada Education Goal 5: All students have access to new and continued educational opportunities supported by funding that is administered transparently consistently and in accordance with legislative or grant guidelines
Nevada Education Goal 6: All students and adults learn and work together in safe environments where identities and relationships are valued and celebrated